## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | Sprint_3
1.01 | As a partner I can submit a description of a task so that admin can post my describtion | 3 | Ashraf | Dardir | Hossam | test
1.02 | As a partner I choose the consultancy agency to proceed with so that I take one which satisfies me | 2 | Ashraf | Dardir | Hossam | test
1.03 | As a candidate I can recieve notification of my acceptance and recieve the task's orientation invitation so that I can know to start implement or not | 13 | Beltagy | Islam | Mohaned | test
1.04 | As a candidate I can view tasks so that I can see every task/project in platform | 2 | Maher | Dardir | Hossam | test
1.05 | As a candidate I can apply for the tasks if I'm eligible so that I can start work on them if my application is accepted | 3 | Maher | Dardir | Hossam | test
1.06 | As a consultancy agency I can view decriptions of partners asking for consultancy so that I can help them | 2 | Maher | Dardir | Hossam | test
1.07 | As an admin I can recieve notification that a new description for a project is submitted by lirten Hub's Partner so that I can see every task and give my feedback | 13 | Soror | Islam | Mohaned | test
1.08 | As an admin I can post the description of a task defining attributes so that candidate can aply for it | 3 | Ashraf | Dardir | Hossam | test
1.09 | As an admin I can review the description so that I can accept or reject or ask for modify them. | 2 | Ashraf | Dardir | Hossam | test
1.1 | As a consultancy agency I can submit a description so that admin can negotiate | 3 | Ashraf | Dardir | Hossam | test
1.11 | As an admin I can see all applications so that I can assign the the best contributor for this task | 2 | Beltagy | Islam | Mohaned | test
1.12 | As an admin I can decide who will be assigned to the task so that the task is implemented | 3 | Soror | Islam | Mohaned | test
1.13 | As a partener I can submit a description of a task defining attributes so that I can define every small thing in my task if I don't want consaltancy egency | 3 | Ashraf | Dardir | Hossam | test
1.14 | As a partner I can recieve the final product so that I can download its files | 3 | Maher | Dardir | Hossam | test
1.15 | As a partner I can view the profile of a member so that I can see his experience | 2 | Islam | Ashry | Omar | test
1.16 | As a partner I am able to see the tasks timeline so that I can see its current state | 2 | Maher | Dardir | Hossam | test
1.17 | As a partner I can view the profile of Consultancy agency so that I can see its experience | 2 | Mohaned | Ashry | Omar | test
1.18 | As an admin I am able to see the life cycle state of the tasks that i am handling so that I know the current state of the task | 2 | Maher | Dardir | Hossam | test
1.19 | As a candidate I can submit the final product so that partner can take their work | 3 | Dardir | Beltagy | Soror | test
1.2 | As a consultancy agency I am able to see the life cycle state of the tasks that i am assigned to so that I know the current state of the task | 2 | Dardir | Beltagy | Soror | test
1.21 | As a candidate I can search for tasks by category so that I can select task based on my experience field | 5 | Hossam | Beltagy | Soror | test
1.22 | As a candidate I can search for tasks by required years of experience so that I can select good task according to my experience level | 5 | Hossam | Beltagy | Soror | test
1.23 | As a candidate I can search for tasks by itʼs monetary compensation so that I can select tasks which need a lot of work or not | 5 | Dardir | Beltagy | Soror | test
1.24 | As a candidate I can view recommendations of tasks that matches my skills so that it help me to don't wast my time searching about tasks | 5 | Hossam | Beltagy | Soror | test
1.25 | As a partner I can review (rate) the consultant after the product delivery so that others know its experience | 3 | Dardir | Beltagy | Soror | test
1.26 | As a partner I can edit the descrbtion if it's rejected so that admin can accept or reject again | 3 | Maher | Ashraf | Maher | test
1.27 | As a partner I can review(rate) the freelancer after the product delivery so that others know its experience | 3 | Dardir | Beltagy | Soror | test
1.28 | As an admin I can organize an event so that I can put it in platform | 2 | Soror | Islam | Mohaned | test
1.29 | As an admin I can accept requests so that partner can put there events in platform if it satisfy our standards | 3 | Ashry | Dardir | Hossam | test
1.3 | As a partner I can submit a request to organize an event so that I can put it in platform | 2 | Ashry | Ashraf | Maher | test
1.31 | As a member I can view events so that I can be able to see all events in platform | 5 | Ashry | Ashraf | Maher | test
1.32 | As a member I can see the details of the event( itʼs location, description, registration price, remaining places, speakers and topics cover as well as whether they can apply or not.) so that I can know all information about them | 2 | Ashry | Ashraf | Maher | test
1.33 | As a member I can search for events by type so that I can select event based on my interests | 5 | Ashry | Ashraf | Maher | test
1.34 | As a member I can search for events by location s that I can select events near to my location | 5 | Omar | Ashraf | Maher | test
1.35 | As a member I can book a place based on the event type and free spaces so that I can attend the event | 5 | Omar | Ashraf | Maher | test
1.36 | As a member when i attend an event it should be added to my history of attended events in my profile after the event so that I can receive recommendation events based on them | 5 | Islam | Ashry | Omar | test
1.37 | As a member I can rate the event so that partner can improve their events in futer | 2 | Dardir | Beltagy | Soror | test
1.38 | As a member I can send feedback to the organizing entity using a form sent so that partner can improve their events in futer | 3 | Omar | Ashraf | Maher | Implement/test
1.39 | As a member I am recommended events based my interests, past attended events and location so that it help me to don't waste my time searching about events | 5 | Ashry | Ashraf | Maher | Implement/test
2
2.1 | As a user I can edit my profile so that I can update it with latest info | 5 | Islam | Ashry | Omar | test
2.2 | As an admin I can edit my profile so that it has my latest info | 3 | Islam | Ashry | Omar | test
2.3 | As a member I should be able to view past attended events so that I know my event history | 5 | Mohaned | Ashry | Omar | test
2.4 | As a partener I should be able to view events organized by me so that I know my events | 5 | Mohaned | Ashry | Omar | test
2.5 | As a member I should be able to view past projects so that others can see my completed tasks | 5 | Mohaned | Ashry | Omar | test