## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | As a partnenr i can Create a task request | 3 | ashraf | -
2 | As a partnenr i can Read a task request | 2 | ashraf | -
3 | As a partnenr i can Update a task request | 5 | ashraf | -
4 | As a partnenr i can Delete a request | 3 | ashraf | -
5 | As an admin i should recieve a notification once a partner created a task request(Notification created) | 3 | soror | 1 | As a partner when I create a task request I can notify others
6 | As a partner i can Create an event request | 3 | omar | -
7 | As a partner i can Read an event request | 2 | omar | -
8 | As a partner i can Update an event request | 3 | omar | -
9 | As a partner i can Delete an event request | 3 | omar | -
10 | As a partner i can create my profile | 3 | soror | -
11 | As a partner i can read my profile | 2 | soror | -
12 | As a partner i can update my profile | 5 | soror | -
13 | As a partner i can delete my profile | 3 | soror | -
14 | As a partner i can create review | 3 | hossam | 28,51 | a partner review a member or a consultancy associated with his task
15 | As a partner i can read review | 2 | hossam | -
16 | As a partner i can update review | 5 | hossam | -
17 | As a partner i can delete review | 3 | hossam | -
18 | As a candidate i can Read a notification | 2 | soror | -
19 | As a candidate i can Read a task | 2 | ashry | -
20 | As a candidate i can Create an Application to apply on a task | 3 | bltagy | 35 | when admin creates a task a candidate should be able to apply on it
21 | As a candidate i can Read an Application | 2 | bltagy | -
22 | As a candidate i can update an Application | 5 | bltagy | -
23 | As a candidate i can Delete an Application | 3 | bltagy | -
24 | As a consultancy agency I can Create a task request | 3 | ashry | 1 | as a consultancy I should be able to create a task request when a partner choses me as a consultancy agency
25 | As a consultancy agency I can Read task request | 2 | ashry | -
26 | As a consultancy agency I can Update task request | 5 | ashry | -
27 | As a consultancy agency I can Delete task request | 3 | ashry | -
28 | As a consultancy i can create my profile | 5 | islam | -
29 | As a consultancy i can read my profile | 2 | islam | -
30 | As a consultancy i can update my profile | 8 | islam | -
31 | As a consultancy i can delete my profile | 3 | islam | -
32 | As a partner i can Recieve a notification once an admin accepts the submitted description(Notification created) | 3 | soror | 35 | when an admin creates a task, the partner gets notified
33 | As an admin i can Read a notification | 2 | soror | -
34 | As an admin i can Read an Application | 2 | bltagy | -
35 | As an admin i can Create a task | 3 | ashry | 1,24 | when a partner or a consultancy creates a task request the a dmin can create a task
36 | As an admin i can Read a task | 2 | ashry | -
37 | As an admin i can Update a task | 5 | ashry | -
38 | As an admin i can Delete a task | 3 | ashry | -
39 | As an admin i can Read a task request | 2 | ashry | -
40 | As an admin i can Create an event | 3 | maher | 6 | when a partner requests to make an event the admin can create the event
41 | As an admin i can Read an event | 2 | maher | -
42 | As an admin i can Update an event | 5 | maher | -
43 | As an admin i can Delete an event | 3 | maher | -
44 | As an admin i can Read an event request | 2 | omar | -
45 | As an admin i can Update an event request acceptence status | 5 | omar | -
46 | As a admin i can create my profile | 5 | mohaned | -
47 | As a admin i can read my profile | 2 | mohaned | -
48 | As a admin i can update my profile | 8 | mohaned | -
49 | As a admin i can delete my profile | 3 | mohaned | -
50 | As an admin i can read review | 2 | hossam | -
51 | As a member can create my profile | 3 | dardir | -
52 | As a member can read my profile | 2 | dardir | -
53 | As a member can update my profile | 5 | dardir | -
54 | As a member can delete my profile | 3 | dardir | -
55 | As a member i can Read an event | 2 | maher | -
56 | As a member i can create review | 3 | hossam | 28,51,40 | a member can review an event that is created
57 | As a member i can read review | 2 | hossam | -
58 | As a member i can update review | 5 | hossam | -
59 | As a member i can delete review | 3 | hossam | -
60 | As a member i can create a booking for an event | 2 | maher | 40 | when an admin creates an event as a member I can book a place in it
61 | As a member i can read a booking for an event | 2 | maher | --
62 | As a member i can update a booking for an event | 3 | maher | --
63 | As a member i can delete a booking for an event | 3 | maher | --