## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1.01 | As a partner I can submit a description of a task (task request) so that admin can post my description REACT | 3 | Ashraf | Islam | Mohaned
1.02 | as a member I can use google location api to know near events | 10 | Maher | Islam | Mohaned
1.03 | As a member I can receive notification of my acceptance so that I can know to start implement or not REACT | 8 | Soror | Islam | Mohaned
1.04 | As a member I can view tasks so that I can see every task/project in platform REACT | 5 | Beltagy | Dardir | Hossam
1.05 | As a member I can apply for the tasks if I'm eligible so that I can start work on them if my application is accepted REACT | 8 | Mohannad | Dardir | Hossam
1.06 | as a member I can see all events so that I know if something interests me is coming | 5 | Beltagy | Islam | Mohaned
1.07 | As an admin I can receive notification that a new project description is submitted by a Partner so that I decide on it REACT | 8 | Soror | Islam | Mohaned
1.08 | As an admin I can post the description of a task defining attributes so that member can apply for it REACT | 3 | Ashraf | Dardir | Hossam
1.09 | As an admin I can review the description so that I can accept or reject or ask for modify them REACT | 8 | Ashraf | Dardir | Hossam
1.1 | As a consultancy agency I am able to see the life cycle state of the tasks that i am assigned to so that I know the current state of the task REACT | 5 | Beltagy | Islam | Mohaned
1.11 | As a partner I can see my tasks so that I know info about them | 5 | Beltagy | Islam | Mohaned
1.12 | As a partner I can submit a description of a task if I don’t need a consultancy so that admin can post my description REACT | 3 | Ashraf | Dardir | Hossam
1.13 | As a partner I am able to see the tasks timeline so that I can see its current state REACT | 3 | Maher | Dardir | Hossam
1.14 | As an admin I am able to see the life cycle state of the tasks that i am handling so that I know the current state of the task REACT | 2 | Maher | Dardir | Hossam
1.15 | As a consultancy agency I am able to see the life cycle state of the tasks that i am assigned to so that I know the current state of the task REACT | 2 | Maher | Ashry | Omar
1.16 | As a member I can search for tasks by category so that I can select task based on my experience field REACT | 5 | Hossam | Ashry | Omar
1.17 | As a member I can search for tasks by required years of experience so that I can select good task according to my experience level REACT | 5 | Hossam | Ashry | Omar
1.18 | As a member I can search for tasks by its monetary compensation so that I can select tasks which need a lot of work or not REACT | 5 | Hossam | Ashry | Omar
1.19 | As a partner I can edit the description if it's rejected so that admin can accept or reject again REACT | 3 | Ashraf | Dardir | Hossam
1.2 | As I partner I can choose if I want a consaltancy or not so that I can post a request or task description React | 3 | Ashraf | Islam | Mohaned
1.21 | As an admin I can accept requests so that partner can put there events in platform if it satisfy our standards REACT | 3 | Ashraf | Dardir | Hossam
1.22 | As a partner I can submit a request to organize an event so that I can put it in platform REACT | 2 | Maher | Ashry | Omar
1.23 | As a member I can view events so that I can be able to see all events in platform REACT | 5 | Islam | Ashraf | Maher
1.24 | As a member I can see the details of the event so that I can know all information about them REACT | 2 | Ashry | Ashraf | Maher
1.25 | As a member I can search for events by type so that I can select event based on my interests REACT | 5 | Hossam | Ashraf | Maher
1.26 | As a member I can book a place based on the event type and free spaces so that I can attend the event REACT | 5 | Ashry | Ashraf | Maher
1.27 | As a member when i attend an event it should be added to my history of attended events in my profile after the event so that it’s shown on my profile REACT | 5 | Ashry | Beltagy | Soror
2
2.1 | As a user I can sign up to the web site so that I have an account | 5 | Omar | Beltagy | Soror
2.2 | As a user I can sign in to the web site so that I do my actions | 8 | Omar | Beltagy | Soror
2.3 | As a user I should receive an email after signup | 8 | Omar | Beltagy | Soror
2.4 | As a partner I can see all info of a specific task | 3 | Mohannad | Beltagy | Soror
2.5 | As a member I can see all info of a specific task | 5 | Mohannad | Beltagy | Soror
2.6 | as a member I can use google location api to know near events | 5 | Maher | Beltagy | Soror
2.7 | as a user I can see a nav bar so that I can navigate easily in the website | 5 | Hossam | Ashraf | Maher
2.8 | as a user I should infinitely scroll in the events so that I keep amused by the site | 8 | Islam | Ashraf | Maher
2.9 | as a user I can know more about the company and the site through the about page | 3 | Dardir | Islam | Mohaned
2.1 | as a user I should get notifications using an api so that I know what i’ve missed | 5 | Soror | Ashraf | Maher
2.11 | as a user I can pay online to book an event | 8 | Ashry | Beltagy | Soror
2.12 | as a user I can see some cool visuals so that I enjoy my experience on the site | 8 | Islam | Beltagy | Soror
2.13 | as a user I can see my actions so that I know what I can do on the site | 5 | Mohannad | Ashraf | Maher
2.14 | As a user I can edit my profile so that I can update it with latest info | 5 | Dardir | Ashraf | Maher
2.15 | As an admin I can edit my profile so that it has my latest info | 3 | Dardir | Ashry | Omar
2.16 | As a member I should be able to view past attended events so that I know my event history | 5 | Dardir | Ashry | Omar
2.17 | As a partener I should be able to view events organized by me so that I know my events | 3 | Dardir | Ashry | Omar
2.18 | As a member I should be able to view past projects so that others can see my completed tasks | 2 | Dardir | Ashry | Omar
2.19 | As a partner I can see my requests so that I can keep track of their changes React | 3 | Ashraf | Hossam | Dardir
2.2 | As a partner I can edit my request description so that I can make changes according to the admin's feedback React | 3 | Ashraf | Hossam | Dardir
2.3 | As a partner I can delete my request so that I can remove any unwanted request React | 3 | Ashraf | Hossam | Dardir
2.4 | As an admin I can delete an request so that I can remove any unwanted request | 3 | Ashraf | Hossam | Dardir
2.5 | As an amin I can see all task request so that I can review them | 3 | Ashraf | Hossam | Dardir
2.5 | As a partner I can receive error allerts if I violated any validation of a request so that I can modify my inputs | 2 | Ashraf | Hossam | Dardir
2.6 | As an admin I can receive error allerts if I violated any validation of a request so that I can modify my inputs | 2 | Ashraf | Hossam | Dardir